## Gantt Chart
Dissertation Gantt Chart
Project Timeline ¦ Feb 2026 – Sep 2026 ¦ 17 Deliverables ¦ Submission: 08 Sep 2026
Task | Start Date | End Date | Feb 2026 | Mar 2026 | Apr 2026 | May 2026 | Jun 2026 | Jul 2026 | Aug 2026 | Sep 2026 | Notes / Status
PROJECT INITIATION
Topics Released | 2026-02-03 | 2026-02-03 | ◆ | [7 empty] | W1/S2
Topic Choices Submission | 2026-02-03 | 2026-02-20 | [8 empty] | Due 4:00 PM
Topic Confirmation | 2026-02-26 | 2026-02-26 | ◆ | [7 empty] | Due 4:00 PM
SCOPING & PROPOSAL
Supervisor Meetings & Finalise Scope | 2026-03-04 | 2026-04-16 | [8 empty] | Done by supervisor
Project Proposal Report Submission | 2026-03-04 | 2026-04-16 | [8 empty] | Complete before 16 Apr
INTERIM DELIVERABLES
Prepare 15-min Presentation Slides | 2026-03-15 | 2026-05-07 | [8 empty] | Before presentation week
Proposal Feedback | 2026-04-01 | 2026-05-24 | [8 empty] | Done
Dissertation Proposal Presentation | 2026-05-06 | 2026-05-07 | [8 empty] | Before 07/05/2026
Prepare Interim Report | 2026-05-05 | 2026-06-10 |  |  |  | ◆ |  |  |  |  | Due 4:00 PM
RESEARCH & ANALYSIS
Detailed Literature Review (AWE vs PEMWE and SOFC) | 2026-02-01 | 2026-05-31
Offshore Constraints Analysis (Arven Site in Shetland, Scotland) | 2026-05-01 | 2026-05-31
Technology Comparison Framework Draft | 2026-05-01 | 2026-05-31
Aspen Simulation | 2026-06-01 | 2026-06-30
Synthesis, Conclusions & Research Gaps | 2026-07-01 | 2026-07-31
WRITING & SUBMISSION
Full Dissertation Draft Writing | 2026-06-01 | 2026-07-31
Supervisor Review & Revisions | 2026-07-01 | 2026-08-31
Final Proofreading & Formatting | 2026-08-01 | 2026-08-31
Report Submission | 2026-09-08 | 2026-09-08 | [7 empty] | ◆ | Final deadline
Prepared by:
Syed Yousaf Munib | Research | Writing / Presentation | Review | ◆ Milestone

## Task Data
Task Name | Category | Start Date | End Date | Type | Colour | Notes
Topics Released | PROJECT INITIATION | 2026-02-03 | 2026-02-03 | milestone |  | W1/S2
Topic Choices Submission | PROJECT INITIATION | 2026-02-03 | 2026-02-20 | task | teal | Due 4:00 PM
Topic Confirmation | PROJECT INITIATION | 2026-02-26 | 2026-02-26 | milestone |  | Due 4:00 PM
Supervisor Meetings & Finalise Scope | SCOPING & PROPOSAL | 2026-03-04 | 2026-04-16 | task | teal
Project Proposal Report Submission | SCOPING & PROPOSAL | 2026-03-04 | 2026-04-16 | task | blue | Complete before 16 Apr
Prepare Interim Report (2000 words) | INTERIM DELIVERABLES | 2026-03-15 | 2026-05-04 | task | salmon | Before presentation week
Prepare 15-min Presentation Slides | INTERIM DELIVERABLES | 2026-04-01 | 2026-05-04 | task | salmon | Before 05/05/2026
Dissertation Proposal Presentation | INTERIM DELIVERABLES | 2026-05-05 | 2026-05-05 | milestone |  | W11/S2
Detailed Literature Review (AWE vs PEMWE) | RESEARCH & ANALYSIS | 2026-02-01 | 2026-05-31 | task | blue
Offshore Constraints Analysis (UK Context) | RESEARCH & ANALYSIS | 2026-05-01 | 2026-05-31 | task | blue
Technology Comparison Framework Draft | RESEARCH & ANALYSIS | 2026-05-01 | 2026-05-31 | task | blue
Offshore vs Onshore Route Evaluation | RESEARCH & ANALYSIS | 2026-06-01 | 2026-06-30 | task | blue
Synthesis, Conclusions & Research Gaps | RESEARCH & ANALYSIS | 2026-07-01 | 2026-07-31 | task | grey
Full Dissertation Draft Writing | WRITING & SUBMISSION | 2026-06-01 | 2026-07-31 | task | salmon
Supervisor Review & Revisions | WRITING & SUBMISSION | 2026-07-01 | 2026-08-31 | task | grey
Final Proofreading & Formatting | WRITING & SUBMISSION | 2026-08-01 | 2026-08-31 | task | grey
Report Submission | WRITING & SUBMISSION | 2026-09-08 | 2026-09-08 | milestone |  | Final deadline